## 📋 Overview
AIOps Platform — Product Plan (3 Teams × 12 Weeks)
Platform | AIOps Event Analytics — Network Operations Intelligence
Version | v2.0 Refined (Demo → Production Transition)
Date | April 2026
Teams | Frontend (3–4) · Backend (4–5) · R&D (3–4) = 10–13 Engineers
Timeline | 12 Weeks / 3 Months — April to July 2026
Frontend Stack | Angular 14, TypeScript, RxJS, Angular Material, Chart.js
Backend Stack | Django, Django REST Framework, FastAPI, Kafka, Redis, PostgreSQL
AI/ML Stack | Qwen 3B, scikit-learn, ONNX, PyTorch, vLLM, sentence-transformers
Status | Demo complete. Moving to production implementation.
Sheet | Content | Purpose
📋 Overview | This sheet | Platform summary, teams, tech stack
🧩 Module Master | All 40 modules | Priority, status, team, phase
📅 Timeline | 12-week plan | Week-by-week tasks per team
📊 Gantt Chart | Visual timeline | Bar chart of all tasks across 12 weeks
🔬 R&D Requirements | Research items | Areas needing investigation
⚡ Benchmarks | Performance SLAs | Demo vs target vs production
👥 Teams | 3 team structure | Roles, skills, ownership
🗺️ Roadmap | 3-phase plan | Phase milestones & deliverables

## 🧩 Module Master
Module Master — All Modules, Priority, Status & Team Ownership
ID | Module | Sub-Module | Description | Priority | Demo Status | Prod Status | Phase | Team
M01 | Dashboard | AIOps Landing Dashboard | Main KPI overview: RCA Insights, SLA Breach Risk, Capacity Risk, Anomalies, Recommended Actions. | P1 | ✅ Done (Mock) | API Integration Needed | Phase 1 | Frontend
M02 | Dashboard | Topology Dashboard | Node-graph: device dependency chains, alarm propagation, event flow stepper. | P1 | ✅ Done (Mock) | Real topology API + WebSocket | Phase 2 | Frontend + Backend
M03 | Dashboard | ROI / KPI Dashboard | MTTR reduction, automation rate, cost avoidance, SLA compliance trends. | P2 | ✅ Done (Static) | Finance API integration | Phase 3 | Frontend + Backend
M04 | Events | Event List & Filtering | Paginated event table with multi-field filters. | P1 | ✅ Done (Mock) | Real NMS/SNMP event feed | Phase 1 | Frontend + Backend
M05 | Events | Event Actions | Per-event actions: RCA & Impact sidebar, Probable Cause chain. | P1 | ✅ Done | Link to live RCA API | Phase 1 | Frontend
M06 | Admin | Platform Configuration | Global settings: thresholds, tenant config, integrations. | P1 | ⚠️ Placeholder | Full config API + RBAC | Phase 2 | Backend
M07 | Admin | Knowledge Base (KB) | KB entries with vector embeddings. View/edit individual records. | P1 | ✅ Done (Mock) | Vector DB write/read API | Phase 1 | Backend + R&D
M08 | Admin | Correlation Patterns | PatternGallery: view, enable/disable learned correlation rules. | P1 | ✅ Done (Mock) | Pattern registry API | Phase 2 | Backend + R&D
M09 | Admin | ML Training Config | Scope selection, algorithm selection, duration config. | P1 | ✅ Done (Mock) | Real training job submission API | Phase 2 | Frontend + R&D
M10 | Admin | Training Analysis | Per-model terminal streaming for all ML algorithms. | P1 | ✅ Done (Simulated) | Real training job status API | Phase 2 | Frontend + R&D
M11 | Admin | Training Results | List completed training runs; filter by scope/date. | P2 | ✅ Done (Local) | DB-backed results store | Phase 3 | Backend
M12 | Admin | Training Reports | Full drill-down per run: algorithm outputs, metrics. | P2 | ✅ Done (Static Data) | Dynamic report from model artifacts | Phase 3 | Backend + R&D
M13 | Playground | RCA Playground (7-Step) | Upload event file → 7-step pipeline → animated results. | P1 | ✅ Done (API stub) | Full backend pipeline integration | Phase 1 | Frontend + Backend + R&D
M14 | Playground | Event Deduplication Lab | 6 dedup techniques interactive demo. | P1 | ✅ Done (Mock) | Real dedup engine API calls | Phase 2 | Frontend + Backend
M15 | Playground | Event Suppression Lab | 12 suppression policies demo. | P1 | ✅ Done (Mock) | Real suppression engine API | Phase 2 | Frontend + Backend
M16 | Playground | Bulk Event Processing | Batch run suppression + dedup on large event volumes. | P2 | ⚠️ Partial | File upload API + batch job | Phase 2 | Backend
M17 | Playground | Live Inference Engine | 30s poll cycle, 13 ML model artifacts, failure chain matching. | P1 | ✅ Done (Simulated) | Real model serving + live telemetry | Phase 2 | R&D + Backend
M18 | Core Engine | Event Pre-Processing | Dedup + suppress + normalize raw NMS alarms. | P1 | ⚠️ Design Only | Production streaming processor (Kafka) | Phase 1 | Backend
M19 | Core Engine | Event Correlation Engine | Temporal, Spatial, Topological, Causal, ML/GNN, LLM Semantic. | P1 | ⚠️ Partial Design | Graph correlation engine | Phase 1 | Backend + R&D
M20 | Core Engine | RCA Orchestration | Incident + Goal creation from correlated cluster. | P1 | ✅ Done (API stub) | Real incident management | Phase 1 | Backend
M21 | Core Engine | RCA Intent Router | Score each intent by signal threshold + log keywords. | P1 | ✅ Done (API stub) | Production intent library, LLM scoring | Phase 1 | R&D + Backend
M22 | Core Engine | RCA Hypothesis Scorer | Score hypotheses: signal + log = total. Select top. | P1 | ✅ Done (API stub) | Dynamic hypothesis expansion | Phase 1 | R&D
M23 | Core Engine | RCA Situation Builder | Build situation card + vector embedding to DB. | P1 | ✅ Done (API stub) | Vector DB integration | Phase 1 | Backend + R&D
M24 | Core Engine | RCA Planner LLM | Plan tool calls for diagnostic steps (future). | P2 | ❌ Not Active | Qwen 3B tool-call R&D | Phase 3 | R&D
M25 | Core Engine | RCA Historical Retriever | Vector similarity search in KB. Top-N retrieval. | P1 | ✅ Done (API stub) | Production vector DB | Phase 1 | Backend + R&D
M26 | Core Engine | RCA Correlator LLM | Final RCA via Qwen 3B: root cause + confidence + remedy. | P1 | ✅ Done (API stub) | Qwen 3B production serving | Phase 1 | R&D + Backend
M27 | Core Engine | Remediation Engine | Guided Remediation: Playbook, step states, AI assistant. | P1 | ✅ Done (Simulated) | Real device execution API | Phase 2 | Backend + R&D
M28 | AI/ML | Random Forest Predictor | 150-tree ensemble per device type. | P1 | ✅ Model Artifacts | ONNX conversion, model serving | Phase 2 | R&D
M29 | AI/ML | Anomaly Detection (IF) | Isolation Forest 5% contamination per device type. | P1 | ✅ Model Artifacts | Drift detection, auto-retraining | Phase 2 | R&D
M30 | AI/ML | K-Means Clustering | k=4 behavioral clusters per device type. | P1 | ✅ Model Artifacts | Auto k-selection, drift monitoring | Phase 2 | R&D
M31 | AI/ML | Sequence Mining | Frequent 3-event patterns (support≥2, lift≥1.5). | P1 | ✅ Done (Static) | Real event stream mining | Phase 2 | R&D
M32 | AI/ML | Cross Correlation | Lagged Pearson & Spearman for metric pairs. | P1 | ✅ Done (Static) | Real-time sliding window service | Phase 2 | R&D
M33 | AI/ML | Granger Causality | F-test + OLS for directional metric causality. | P1 | ✅ Done (Static) | Streaming Granger service | Phase 2 | R&D
M34 | AI/ML | Failure Chain Patterns | 4 templates for step-by-step chain matching. | P1 | ✅ Done (Hardcoded) | Dynamic template learning | Phase 2 | R&D
M35 | Infrastructure | SNMP / Syslog Ingestion | Real-time NMS event ingestion pipeline. | P1 | ❌ Not Built | Kafka + SNMP trap + Syslog parser | Phase 1 | Backend
M36 | Infrastructure | Telemetry Store (TSDB) | Time-series metric storage for ML features. | P1 | ❌ Not Built | InfluxDB / TimescaleDB | Phase 1 | Backend
M37 | Infrastructure | Vector Database | Situation card embedding storage + KB retrieval. | P1 | ❌ Not Built | Qdrant / ChromaDB — R&D eval | Phase 1 | Backend + R&D
M38 | Infrastructure | API Gateway | Unified REST API with auth, rate limiting. | P1 | ❌ Not Built | FastAPI + Kong/Nginx | Phase 1 | Backend
M39 | Infrastructure | Auth & RBAC | Multi-tenant auth, role-based access control. | P1 | ❌ Not Built | Keycloak / Auth0 | Phase 1 | Backend
M40 | Infrastructure | LLM Serving (Qwen 3B) | Local LLM inference for RCA pipeline. | P1 | ❌ Not Built | vLLM / Ollama, GPU server | Phase 1 | R&D + Backend

## 📅 Timeline
3-Month Timeline — Week-by-Week Plan (Frontend · Backend · R&D)
Week | Phase | Frontend Tasks | Backend Tasks | R&D Tasks | Milestone | Deliverable
W1 (Apr 13) | Phase 1 | Auth login page & route guards Dashboard API integration scaffold | API Gateway setup (FastAPI + Nginx) Auth service (JWT + RBAC middleware) Kafka cluster deployment | Qwen 3B local serving setup (vLLM/Ollama) Vector DB evaluation PoC (Qdrant vs Chroma) | 🏁 Infra Bootstrap | API Gateway live, Auth working, Kafka running
W2 (Apr 20) | Phase 1 | Event list → real API integration RCA Sidebar → wire to cluster API | SNMP trap receiver + Syslog parser v1 Event normalization pipeline TSDB setup (InfluxDB/TimescaleDB) | Qwen 3B benchmarking (latency, throughput, VRAM) Vector DB selection finalized | 📡 Ingestion Online | Raw events flowing into Kafka
W3 (Apr 27) | Phase 1 | Dashboard KPI widgets → live API data Event filtering → backend query params | Dedup engine: SHA256 + State Transition Suppression engine: Maintenance Window + Flap KB CRUD API (GET/POST/PUT/DELETE) | Intent library expansion (10→30 intents) Hypothesis library expansion Embedding pipeline for KB | 🔧 Pre-Processing Engines | Dedup + Suppression functional
W4 (May 04) | Phase 1 | RCA Playground → full backend integration KB page → real CRUD forms | Temporal + Causal correlation engine RCA Orchestrator API (POST /rca/run) RCA Intent Router API | Qwen 3B intent scoring integration Vector DB write pipeline for situations Situation embedding generation | 🧠 RCA Pipeline v1 | Steps 0-2 working end-to-end
W5 (May 11) | Phase 1 | RCA Playground → animated step results Event actions → live RCA trigger | RCA Hypothesis Scorer API RCA Situation Builder API Vector DB similarity search API | Qwen 3B hypothesis scoring Historical retriever: vector search RCA Correlator: final LLM call | 🎯 Full RCA Pipeline | All 7 RCA steps functional
W6 (May 18) | Phase 1 | Dashboard real-time refresh (polling) Error handling & toast notifications Sidebar nav polish | Parent-Child topology suppression Redis caching layer for dedup Audit logging for all actions | RCA accuracy validation & tuning Prompt engineering for better RCA output Context window optimization | ✅ Phase 1 Complete | Core platform demo-ready
W7 (May 25) | Phase 2 | Topology Dashboard → dynamic API data Clickable nodes → event drill-down Remediation Sidebar → wire to API | Remediation playbook execution API Device connection pool (SSH/Netconf) Topological correlation (graph-based) | Random Forest → ONNX conversion Isolation Forest → ONNX conversion K-Means → ONNX serving | 🔌 Topology + Remediation | Topology live, Remediation API ready
W8 (Jun 01) | Phase 2 | Training Config → server-side job submit Training Analysis → SSE log streaming Dedup Lab → real API wiring | Model Training API (POST /train/start) Training Status SSE streaming Semantic Dedup (LLM embeddings) | Sequence Mining on real event streams Cross Correlation sliding window Granger Causality streaming service | 📊 Training Pipeline | ML training jobs submittable
W9 (Jun 08) | Phase 2 | Suppression Lab → real engine API Live Inference → real model polling Bulk event processing UI | Suppression: Dynamic Threshold (p95) Model Artifact Registry (MLflow) Rollback engine for remediation | Failure chain dynamic learning Live inference: 13 model serving Confidence jump logic tuning | 🤖 Intelligence Layer | Live inference operational
W10 (Jun 15) | Phase 2 | Correlation Patterns → enable/disable WebSocket/SSE for real-time dashboard Dark/light mode persistence | Pattern registry API (CRUD + toggle) Remedy safety guardrails v1 Event bulk-select actions API | GNN correlation cluster refinement Feedback loop: operator confirms/rejects RCA LLM tool-call evaluation (Planner R&D) | ✅ Phase 2 Complete | Full intelligence + operations layer
W11 (Jun 22) | Phase 3 | ROI/KPI Dashboard → finance API Training Results → DB-backed list Export to CSV/PDF | Multi-tenancy data isolation Retraining scheduler (drift trigger) ITSM ticket integration (ServiceNow/Jira) | Fine-tuning Qwen 3B on network domain XAI: SHAP values for RF predictions Model drift detection pipeline | 💼 Business Value | ROI dashboard, multi-tenancy
W12 (Jun 29) | Phase 3 | Training Reports → dynamic drill-down Performance optimization (Lighthouse) Final UI polish & responsive fixes | Performance tuning (load testing) Security audit & penetration testing Documentation & API specs | Performance: inference at scale (batching) A/B testing framework for models Final model accuracy benchmarking | 🚀 Production Ready | Platform ready for deployment

## 📊 Gantt Chart
Gantt Chart — 12-Week Project Timeline (Frontend · Backend · R&D)
Task | Team | W1 Apr 13 | W2 Apr 20 | W3 Apr 27 | W4 May 04 | W5 May 11 | W6 May 18 | W7 May 25 | W8 Jun 01 | W9 Jun 08 | W10 Jun 15 | W11 Jun 22 | W12 Jun 29
── Frontend Team ──
Auth Login & Route Guards | Frontend | █████
Dashboard API Integration | Frontend | █████ | █████ | █████
Event List & Filtering → API | Frontend |  | █████ | █████
RCA Sidebar → Live API | Frontend |  | █████ | █████ | █████ | █████
RCA Playground Integration | Frontend |  |  |  | █████ | █████
KB CRUD Forms | Frontend |  |  |  | █████
Error Handling & Polish | Frontend | [5 empty] | █████
Topology Dashboard (Dynamic) | Frontend | [6 empty] | █████
Remediation Sidebar → API | Frontend | [6 empty] | █████ | █████
Training Config & Analysis UI | Frontend | [7 empty] | █████ | █████
Dedup/Suppression Labs → API | Frontend | [7 empty] | █████ | █████
Live Inference UI | Frontend | [8 empty] | █████ | █████
WebSocket/SSE Real-Time | Frontend | [9 empty] | █████
ROI Dashboard & Reports | Frontend | [10 empty] | █████ | █████
Final Polish & Optimization | Frontend | [11 empty] | █████
── Backend Team ──
API Gateway + Auth + Kafka | Backend | █████
SNMP/Syslog Ingestion | Backend |  | █████ | █████
TSDB Setup & Integration | Backend |  | █████
Dedup Engine (SHA256/State) | Backend |  |  | █████
Suppression Engine | Backend |  |  | █████ | █████
KB CRUD API | Backend |  |  | █████
Correlation Engine | Backend |  |  |  | █████ | █████
RCA Pipeline APIs (Steps 0-6) | Backend |  |  |  | █████ | █████
Redis Caching + Audit Log | Backend | [5 empty] | █████
Remediation Execution API | Backend | [6 empty] | █████ | █████
Device Connection Pool | Backend | [6 empty] | █████ | █████
Training API + SSE Streaming | Backend | [7 empty] | █████
Semantic Dedup + Threshold | Backend | [7 empty] | █████ | █████
Model Registry (MLflow) | Backend | [8 empty] | █████
Pattern Registry + Safety | Backend | [9 empty] | █████
Multi-Tenancy + ITSM | Backend | [10 empty] | █████
Security Audit + Perf Tuning | Backend | [11 empty] | █████
── R&D Team ──
Qwen 3B Local Setup | R&D | █████ | █████
Vector DB Evaluation | R&D | █████ | █████
Intent & Hypothesis Libraries | R&D |  |  | █████ | █████
Embedding Pipeline | R&D |  |  | █████ | █████
Qwen 3B Scoring Integration | R&D |  |  |  | █████ | █████
RCA LLM Pipeline Testing | R&D |  |  |  |  | █████ | █████
ONNX Model Conversion | R&D | [6 empty] | █████
Sequence Mining + Cross Corr | R&D | [7 empty] | █████
Granger Causality Streaming | R&D | [7 empty] | █████ | █████
Failure Chain Learning | R&D | [8 empty] | █████
Live Inference Serving | R&D | [8 empty] | █████ | █████
GNN Correlation R&D | R&D | [9 empty] | █████
LLM Fine-Tuning (LoRA) | R&D | [10 empty] | █████ | █████
XAI + Drift Detection | R&D | [10 empty] | █████ | █████
Scale Testing + Benchmarks | R&D | [11 empty] | █████
MILESTONES |  | 🏁 Infra Bootstrap | 📡 Ingestion Online |  | 🧠 RCA Pipeline v1 |  | ✅ Phase 1 Complete | 🔌 Topology + Remediation |  |  | ✅ Phase 2 Complete |  | 🚀 Production Ready
Legend:
█████ | Frontend
█████ | Backend
█████ | R&D
◆ | Milestone

## 🔬 R&D Requirements
R&D Requirements — Research, PoC & Unknowns
ID | Area | Priority | Risk | Description | Resources | Timeline | Owner
R01 | LLM — Qwen 3B Serving | P1 | HIGH | Deploy Qwen 3B on local GPU (vLLM/Ollama). Benchmark: latency <3s, throughput >5 req/s. Evaluate Q4/Q8. | GPU server (≥24GB VRAM), benchmark suite | W1–W2 | R&D
R02 | LLM — Tool-Call / Function Calling | P2 | HIGH | Evaluate Qwen 3B structured tool-call output for Planner LLM step. | Qwen 3B access, incident test dataset | W10 | R&D
R03 | LLM — Domain Fine-Tuning | P2 | MEDIUM | Fine-tune on network incident logs/RCA reports. LoRA/QLoRA approach. | GPU cluster, 5000+ labeled pairs | W11–W12 | R&D
R04 | Vector DB Selection | P1 | HIGH | Evaluate ChromaDB vs Qdrant vs Weaviate. Criteria: speed, multi-tenancy, scale. | 3 PoCs, benchmark tool | W1–W2 | R&D + Backend
R05 | GNN Correlation | P3 | HIGH | Graph Neural Network for topology-aware cluster refinement. | GPU, topology dataset, PyG/DGL | W10 | R&D
R06 | Granger at Scale | P2 | MEDIUM | Streaming Granger causality: 50+ metrics × 100+ devices in real-time. | Real telemetry, Flink/Spark | W8–W9 | R&D
R07 | Dynamic Failure Chains | P2 | HIGH | Auto-discover new failure chain templates from production data. | Event history, mining pipeline | W9 | R&D
R08 | Intent Library Expansion | P1 | MEDIUM | Expand from ~10 to 50+ intents covering BGP, OSPF, MPLS, QoS, Security. | Network SMEs, labeled incidents | W3–W4 | R&D
R09 | Remediation Safety | P1 | CRITICAL | Dry-run mode, impact assessment, approval workflow, rollback plan. | Security architects | W7–W10 | Backend + R&D
R10 | SNMP/Syslog Normalization | P1 | HIGH | Parse 20+ vendor formats to canonical schema. | MIB files, parser framework | W2–W3 | Backend
R11 | Feedback Loop | P2 | MEDIUM | Operator confirms/rejects RCA → retrain models. Closed-loop learning. | Feedback UI, retraining pipeline | W10 | R&D + Frontend
R12 | Inference at Scale | P2 | HIGH | Batch/cache 13 model calls; ONNX optimization for 100s of devices. | ONNX Runtime, load testing | W12 | R&D

## ⚡ Benchmarks
Performance Benchmarks — Demo vs Target vs SLA
Component | Metric | Demo Value | Target (Prod) | SLA | Method | Notes
Qwen 3B LLM | Single inference latency | N/A (no GPU) | < 3 seconds | < 5s (P95) | curl / wrk2 | Q4 quantized recommended
Qwen 3B LLM | Throughput (req/s) | N/A | ≥ 5 req/s | ≥ 3 req/s | locust load test | vLLM batch scheduler
Qwen 3B LLM | GPU Memory (VRAM) | N/A | ~8 GB (Q4) | < 24 GB | nvidia-smi | RTX 3090/4090 or A100
RCA Pipeline (7 Steps) | End-to-end latency | ~2s (stub) | < 10 seconds | < 15s (P95) | E2E API timer | Step 6 LLM dominates
Event Ingestion | Throughput (events/s) | N/A (mock) | ≥ 10,000 evt/s | ≥ 5,000 evt/s | Kafka bench | Partitioning critical
Dedup Engine | Throughput | N/A | ≥ 5,000 evt/s | ≥ 2,000 evt/s | JMeter/locust | Redis SET O(1)
Correlation Engine | Cluster formation | N/A | < 1 second | < 2 seconds | API timer | 15min sliding window
Random Forest | Prediction latency | < 50ms | < 10ms (ONNX) | < 20ms | pytest-benchmark | ONNX Runtime
Vector DB Search | Top-5 retrieval | N/A | < 50ms | < 100ms | Qdrant bench | 1M+ embeddings
Live Inference | Poll cycle (30 dev) | ~500ms (sim) | < 5 seconds | < 10 seconds | E2E timer | Parallel calls
API Gateway | REST latency | N/A | < 200ms | < 500ms (P99) | k6 load test | Excludes LLM
Frontend | Page load (LCP) | ~1.2s | < 2 seconds | < 3 seconds | Lighthouse | Angular production build

## 👥 Teams
Team Structure — 3 Teams: Frontend · Backend · R&D
Team | Focus Area | Modules Owned | Members | Required Skills
Frontend Team | Angular 14/TypeScript UI Development | Dashboard, Events, Admin Pages, Playground UI, RCA Sidebar, Remediation Sidebar, Auth UI, Topology Viz | 3–4 Engineers | Angular 14, TypeScript, RxJS, Chart.js, Angular Material, WebSocket/SSE, CSS/SCSS
Backend Team | Django/FastAPI Core APIs, Infrastructure & Services | Event Ingestion, Kafka, Dedup/Suppression Engines, Correlation Engine, RCA Pipeline APIs, KB CRUD, Remediation Execution, Auth/RBAC, API Gateway, TSDB, Vector DB, CI/CD | 4–5 Engineers | Django, Django REST Framework, FastAPI, Kafka, Redis, PostgreSQL, Docker, K8s, Nginx/Kong
R&D Team | AI/ML Research, Model Training, LLM Integration & Innovation | Qwen 3B Serving, RF/IF/KMeans Models, Granger Causality, Sequence Mining, GNN Correlation, Fine-Tuning, Failure Chain Learning, XAI, Drift Detection, Vector Embeddings | 3–4 Engineers/Researchers | PyTorch, scikit-learn, ONNX, vLLM, sentence-transformers, PyG/DGL, LoRA/QLoRA, MLflow

## 🗺️ Roadmap
Production Roadmap — 3 Phases / 12 Weeks
Phase | Name | Duration | Key Milestones | Modules | Status
Phase 1 | Foundation & Core Pipeline | Weeks 1–6 (6 weeks) | Real event ingestion, dedup, suppression, correlation, full 7-step RCA, KB, vector DB, auth, API gateway | M01,M04,M05,M07,M13,M18–M26,M35–M40 | ⬜ Not Started
Phase 2 | Intelligence & Operations | Weeks 7–10 (4 weeks) | Live inference, training pipeline, remediation engine, topology, production labs, model serving | M02,M08–M10,M14–M17,M27–M34 | ⬜ Not Started
Phase 3 | Business Value & Hardening | Weeks 11–12 (2 weeks) | ROI dashboard, multi-tenancy, training reports, fine-tuning, security audit, performance tuning | M03,M11,M12,M24,R03,R05 | ⬜ Not Started